COMPANION POLICY BRIEF

COMPETITION VALIDATION AND IMPLEMENTATION BRIEF

Historical simulation, ranking validation, athlete-protection standards, legal review, and approval sequencing

| Document role | Status | Date |
| --- | --- | --- |
| Companion to Integrated FBS Competition Reform | Initial analytical framework for stakeholder testing | August 2026 |

Written by Alec Levine. Developed with AI-assisted research, drafting, editing, modeling, and document production. The policy positions, judgments, and responsibility for this framework are Alec Levine’s.

This brief converts the proposal’s open implementation questions into defined tests, decision gates, owners, and work products. It does not move unsettled technical analysis into the core competition proposal.

RECOMMENDATION  Run competition, calendar, welfare, legal, and governance workstreams in parallel, but do not authorize launch until every mandatory gate has an accountable owner, a published result, and an approved mitigation.

# 1. Scope and decision discipline

| Main proposal controls | Companion analysis controls |
| --- | --- |
| Competition architecture, access principles, event hierarchy, and recommended policy | Evidence, assumptions, sensitivities, implementation choices, and unresolved risks |
| Durable Power Four designation and complete National Tournament rules | Historical simulation, dates, workload limits, ranking validation, legal feasibility, and approval instruments |
| CFP priority and no mid-postseason transfer | Economic protection and recognition for qualifying institutions outside the Power Four |

A companion finding changes policy only after the main proposal is formally versioned. This prevents draft assumptions from silently becoming rules.

# 2. Historical simulation protocol

## 2.1 Required season-level dataset

- Final and post-regular-season CFP ranking for every ranked institution, including record and conference affiliation for that season.

- Conference-championship participants, champions, game dates, sites, and results.

- Automatic-qualifier category, independent status, postseason selection, seed, host designation, result, and margin.

- Opponent-strength or rating input sufficient to compare expected path difficulty across benefit tiers.

- Academic-calendar, travel-distance, rest-day, kickoff-window, weather, and campus-availability data for calendar stress testing.

## 2.2 Required tests

| Test | Question | Mandatory output |
| --- | --- | --- |
| Capacity | Do protection and champion claims ever exceed two double byes or eight single byes? | Frequency, affected ranking positions, displaced claimant, and rule used |
| Monotonic benefit | Does any lower benefit band receive an easier expected path than the band above it? | Path-strength distribution by entry tier and seed |
| Access | Which institutions enter through automatic access, at-large access, or the National Tournament? | Season-by-season field and first-four-out list |
| Championship protection | Does playing an additional title game reduce an earned benefit? | Pre-title claim, final position, and counterfactual without protection |
| National Tournament | Are automatic bids, host guarantees, and replacements internally consistent? | Sixteen-team field, host order, replacement order, and excluded-team explanation |
| Postseason exclusivity | Would a CFP-to-secondary transfer create rest or bracket inequity? | Rest-day and opponent-path comparison; policy remains no transfer |

## 2.3 Decision rules for bye conflicts

The main proposal’s provisional hierarchy should remain the base case: designated conference champions first, protected Nos. 3–10 title-game participants second, and final-ranking order third. Backtesting must compare it with two alternatives:

- Strict pre-title order: fill all available protected positions by the post-regular-season ranking, then apply champion guarantees.

- Champion-first with displaced-host protection: apply champion byes first; a displaced protected claimant receives the highest opening-round home position.

- Final-ranking reset: abandon single-bye protection and fill all remaining positions after title games; this is the control case, not the recommended rule.

ADOPTION GATE  Select the rule with the lowest conflict frequency and the clearest monotonic benefit structure. A displaced claimant must never fall below the highest opening-round home position solely because fixed bye capacity was exhausted.

# 3. Ranking methodology validation

## 3.1 Model separation

The National Résumé Rating (current public model: v0.48) measures achievement; the Team Strength Rating estimates present quality. They must be trained, validated, published, and audited separately. Selection remains résumé-led.

| Control | National Résumé Rating | Team Strength Rating |
| --- | --- | --- |
| Primary question | What did the institution earn? | How strong is the team now? |
| Permitted inputs | Results, venue, opponent quality, schedule strength, capped game control | Efficiency, availability, recent performance, predictive indicators |
| Prohibited shortcut | Preseason ranking or ranked-at-the-time labels | Using prediction alone to erase completed wins |
| Published validation | Conference bias, network sensitivity, stability, gaming tests | Out-of-sample accuracy, injury sensitivity, calibration |

Current public evidence comprises twelve time-locked weekly checkpoints across 2024 and 2025. The same 30% Quality-Win Depth, 30% Schedule-Adjusted Record, 20% Loss Integrity, 15% Opponent-Adjusted Performance, and 5% Win Control balance is applied to every team; held-out seasons and the live 2026 run remain adoption gates.

## 3.2 Governance and appeals

- Publish code, data definitions, version history, and an annual independent validation report.

- Correct objective data errors through an expedited process; do not allow an appeal merely because an institution dislikes a properly calculated result.

- Require a written explanation for a committee placement more than three positions outside the published objective résumé range.

- Test outcomes by conference, independent status, schedule network, home/road mix, and late-season availability to identify structural bias.

# 4. Calendar, workload, and athlete-welfare review

| Standard | Proposed floor | Evidence required before launch |
| --- | --- | --- |
| Recovery | At least seven full days between contests; National Tournament opener at least nine days after title games | Medical and performance review of short-week and travel combinations |
| Maximum games | No path above 18 contests; conference expansion must reduce regular-season exposure | Path-by-path game count and practice exposure |
| Travel | Charter-equivalent travel standards, recovery day, and funded family assistance | Distance, time-zone, weather, and return-to-campus model |
| Medical | Independent medical authority, emergency action plan, catastrophic coverage, and adequate host staffing | Site certification and insurance review |
| Academic | No avoidable conflicts with final examinations; tutoring and remote-course access while traveling | Institution-level academic-calendar overlay |
| Roster stability | No general portal, formal signing, or head-coach movement during the championship run | Legal review, exceptions, and emergency process |

STOP CONDITION  A calendar configuration fails if it requires less than the approved recovery floor, produces an unmanaged examination conflict, or relies on a host that cannot satisfy medical and operational standards.

# 5. Legal and labor workstream

This is an issue-spotting and sequencing framework, not legal advice. Qualified counsel and, where applicable, athlete representatives or collective-bargaining parties must approve the final instruments.

| Issue | Question to resolve | Required instrument |
| --- | --- | --- |
| Transfer and roster windows | Can common timing and narrow exceptions be implemented without unlawful restraints? | Bylaw, waiver procedure, and negotiated provisions where required |
| Player agreements | What term, exit, medical, academic, and dispute rights are enforceable? | Model agreement and disclosure standard |
| Revenue and NIL | How do institutional benefits, third-party NIL, and postseason distributions interact? | Payment policy, NIL framework, audit and tax disclosures |
| Employment and bargaining | Which rules are mandatory subjects of bargaining or affected by classification? | Labor analysis and bargaining plan |
| Antitrust | Which joint restraints are necessary, narrowly tailored, and supported by procompetitive evidence? | Competition analysis and evidentiary record |
| State and federal law | Which jurisdictions conflict, preempt, or require special handling? | Fifty-state and federal matrix |

# 6. Governance, sponsorship, and approval sequence

## 6.1 Parallel approval tracks

| Track | Primary parties | Principal subjects |
| --- | --- | --- |
| CFP and commercial | CFP governance, conferences, independent institutions, rights holders, bowls | Field, access, bracket, rights, sites, distributions, and event operations |
| NCAA Division I | FBS Oversight Committee, Division I governance, member conferences and institutions | Playing season, recruiting, roster timing, eligibility, health and safety, and legislation |
| Institutional and conference | Presidents, athletics directors, faculty representatives, campus counsel | Scheduling, academic calendars, host standards, budgets, and local approvals |
| Athlete and labor | Current athletes, athlete representatives, counsel, bargaining representatives where applicable | Workload, movement, agreements, compensation, health, and dispute rights |

## 6.2 Sponsorship package

- One-page decision memorandum identifying the requested authorization and matters reserved for negotiation.

- Main competition proposal with version number, source appendix, and redline against the current structure.

- Historical simulation workbook, methodological memorandum, and independent validation letter.

- Calendar and athlete-welfare certification, legal issue memorandum, and financial/media feasibility framework.

- Draft bylaw concepts, CFP participation-agreement terms, selection protocol, host standards, and transition schedule.

# 7. Implementation instruments and staged workplan

| Stage | Work product | Exit criterion |
| --- | --- | --- |
| 0 · Sponsor formation | Designate conference, institutional, CFP, NCAA, and athlete representatives | Charter, owners, confidentiality rules, and decision rights approved |
| 1 · Evidence build | Historical model, calendar overlay, welfare review, legal map, financial data request | Data completeness and methods signed off |
| 2 · Policy resolution | Decide bye rule, ranking protocol, dates, roster standards, and revenue principles | No unresolved competition-rule contradiction |
| 3 · Instrument drafting | Bylaws, selection and host protocols, commercial terms, model agreements | Counsel and operational review complete |
| 4 · Negotiation and adoption | CFP approvals, NCAA pathway, conference consents, rights negotiations | All required approvals and contractual consents obtained |
| 5 · Parallel-season test | Shadow rankings, mock selections, host audits, media rehearsals | Independent launch-readiness certification |
| 6 · Launch and review | Live operation, incident reporting, annual audit, sunset review | Published first-year report and approved corrections |

# 8. Sources

NCAA, Division I Football — FBS Oversight Committee role

NCAA, Division I Legislation and Policy — legislative pathways

College Football Playoff, Selection Committee Protocol and Voting Process

College Football Playoff, Week-by-Week Selection Committee Rankings

End of brief.